## Tabelle1
Name | description | probability of occurence | impact | risk factor (prob*impact) | risk mitigation | person in charge
Laravel update | Larvel update breaks existing functionality or changes how it should be programmed | 20% | 7 | 1.4 | inform about impact of updates before incorporating and installing, do lots of git commits to avoid having unrecoverable code | Daniel W.
Server crash | server for deployment crashes and is not recoverable | 5% | 8 | 0.4 | Keep backups of the server, avoid doing risky configuration changes | Daniel W.
Documentation overhead | documentation takes much more time than estimated or than programming | 50% | 4 | 2 | Do documentation early and thoroughly | Karl
Illness | members of the team could get ill, they can't work on the project | 30% | 6 | 1.8 | Everyone has to know the code, inform others frequently about development | Daniel R.
Testing deployment | Others are supposed to test the app but can't run it | 20% | 4 | 0.8 | try the "test deployment" often on different machines, good docu | Daniel R.
time deficit | Other classes are too time demanding and we cannot work on the project | 50% | 7 | 3.5 | Do the work early, keep time reserves, do not set the scope too high | Karl
development machines break | One of the laptops used for development has problems and cannot be used anymore, exchange has to be organized | 10% | 9 | 0.9 | Ensure good testing deployment, get know how on Vagrant and Homestead, watch all updates on these | Daniel R.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0