## Tabelle1
Name | description | probability of occurence | impact | risk factor (prob*impact) | risk mitigation | person in charge
time deficit | Other classes are too time demanding and we cannot work on the project | 50% | 7 | 3.5 | Do the work early, keep time reserves, do not set the scope too high | Karl
Documentation overhead | documentation takes much more time than estimated or than programming | 60% | 4 | 2.4 | Do documentation early and thoroughly | Karl
Illness | members of the team could get ill, they can't work on the project | 30% | 6 | 1.8 | Everyone has to know the code, inform others frequently about development | Daniel R.
unfulfillable requirements | The tasks sometimes do not fit all projects, ours as well (e.g. with .feature files/Gherkin) → Making them fit can take a lot of time and is complicated | 60% | 3 | 1.8 | Plan ahead for the Berkling tasks and try to implement functionality, that makes incorporating the tasks easier | Daniel W.
Testing deployment | Others are supposed to test the app but can't run it | 40% | 4 | 1.6 | try the "test deployment" often on different machines, good docu | Daniel R.
Laravel updates | Larvel update breaks existing functionality or changes how functionality has to be implemented (updates are mostly necessary because rest of infrastructure has to get updated as well, so this has to go along that) | 20% | 7 | 1.4 | inform about impact of updates before incorporating and installing, do lots of git commits to avoid having unrecoverable code | Daniel W.
development machines break | One of the laptops used for development has problems and cannot be used anymore, exchange has to be organized | 10% | 9 | 0.9 | Ensure good testing deployment, get know how on Vagrant and Homestead, watch all updates on these | Daniel R.
Server crash | server for deployment crashes and is not recoverable | 5% | 8 | 0.4 | Keep backups of the server, avoid doing risky configuration changes | Daniel W.